## 01 - Requirement Register
IFSCA AML/CFT & KYC Guidelines - Regulatory Change Register ¦ January 2026 Amendments ¦ IBU Compliance Team
Req ID | Clause | Subject | What Changed (Plain Language) | Impact Type | Effort | Priority | Milestone | Owner | Dependency | Status | Notes
REQ-01 | 4.1(d) | Risk categorisation confidentiality | A customer's risk rating and the reasons for it must not be disclosed to the customer under any circumstances. Relationship managers need scripted guidance on how to respond to client queries about account status. | Process / Training | Medium | High | 30 days | Compliance Executive | None | Not Started | Update client communication templates and run RM briefing.
REQ-02 | 5.3(b) | 30-day verification window - escalation to Governing Body | When an IBU cannot complete customer verification within 30 days of establishing a business relationship, it must now formally document the reason and report the non-compliance event to the Governing Body. Previously this was implicit; now it is an explicit obligation. | Process / Policy | High | High | 30 days | Principal Officer | REQ-05 | Not Started | Requires a breach notification template and a Board escalation SOP.
REQ-03 | 5.6 GN(9) | EDD mandatory where beneficial owner is Indian national | Where the beneficial owner of a non-resident entity is an Indian national, the IBU must conduct Enhanced Due Diligence and verify source of funds - regardless of the risk rating assigned to the customer. This is an anti-round-tripping measure and applies to all new and existing NR clients. | Process / Training | High | Critical | 30 days | Compliance Executive | REQ-01 | Not Started | Existing NR client book must be reviewed. Significant workload if IBU has large NR corporate base.
REQ-04 | 5.11 provison | New periodic review cycle for resident Indian clients with FG relationships | For resident Indian customers who have an existing relationship with a Financial Group entity in India, the KYC review cycle changes to 2 years (High risk), 8 years (Medium risk), and 10 years (Low risk). Where FG risk rating differs from the IBU rating, the stricter periodicity applies. | Process / System | High | High | 60 days | Compliance Executive | REQ-05 | Not Started | Client segmentation exercise required. CRM or KYC system may need configuration update.
REQ-05 | 5.11 explanation | KYC periodic updation policy requires Governing Body approval | The policy governing KYC review periodicities must now be formally documented in the IBU's internal KYC policy and approved by the Governing Body. This moves the obligation from an operational practice to a Board-governed document. | Policy | Medium | High | 30 days | Principal Officer | None | Not Started | Draft policy section required before REQ-04 can be closed. Board calendar slot needed.
REQ-06 | 5.11(c)(vii) | Customers must submit updated documents within 30 days of any change | When a customer's KYC documents change (address, identity document renewal, change of directors for legal entities), the customer must notify the IBU and submit updated documents within 30 days. The IBU needs a mechanism to track this and a standard communication to clients. | Process / Training | Medium | Medium | 60 days | Compliance Executive | REQ-05 | Not Started | Client-facing communication template and a tracking mechanism in KYC system required.
REQ-07 | 5.4.4(a) | Legal arrangements - trustees must disclose status at commencement | The obligation to identify persons acting on behalf of a customer has been extended to legal arrangements, including trusts. Trustees must now explicitly disclose their trustee status at the start of the business relationship. Onboarding checklists for trust clients require updating. | Process / Policy | High | High | 60 days | Compliance Executive | REQ-05 | Not Started | Affects family office and trust clients. Onboarding SOP and CDD checklist update required.
REQ-08 | 10.3(5)(a)(i) | STR filing timeline changed from 7 days to 'promptly on conclusion' | The previous 7-day window for filing an STR after concluding suspicion has been removed. Filing must now happen promptly once the Principal Officer concludes a transaction is suspicious. Internal SLA, investigation workflow, and the STR SOP all need to reflect this change. | Process / SOP | High | Critical | 30 days | Principal Officer | None | Not Started | Directly linked to A2 (STR Operations Playbook). Internal SLA must be defined - 'promptly' is not defined in the regulation.
REQ-09 | 5.10(a) proviso | PwD onboarding - rejection requires documented reasoning | Applications from Persons with Disabilities for onboarding or periodic KYC updation cannot be rejected without applying due consideration. The rejecting officer must record their reasons. This applies to both new onboarding and periodic review refusals. | Process / Training | Medium | Medium | 60 days | Compliance Executive | None | Not Started | Onboarding SOP update and staff briefing required. Low frequency but regulatory sensitivity is high.
REQ-10 | Annexure II | V-CIP expanded - new authentication methods and infrastructure standards | The V-CIP framework has been substantially updated. OTP-based Aadhaar e-KYC is now permitted as a verification method. NRI jurisdiction list has been expanded. Infrastructure requirements around IP address controls, liveness checks, and data localisation have been tightened. Any IBU running V-CIP must review its setup against the revised standards. | Process / Training / System | High | High | 90 days | Principal Officer | REQ-05 | Not Started | Requires technology team involvement. If V-CIP is not currently used, this is a lower priority but should still be assessed.
REQ-11 | 1.3.30 | Equivalent e-documents now accepted as OVD for proof of address | Officially Valid Documents for proof of address can now include equivalent e-documents, such as Digilocker-issued documents with valid digital signatures. Document acceptance checklists and onboarding SOPs need to reflect this. Staff must understand what constitutes a valid e-document and how to verify digital signatures. | Process / Training | Medium | Medium | 60 days | Compliance Executive | None | Not Started | SOP and checklist update. Particularly relevant for non-face-to-face onboarding workflows.
REQ-12 | 7.2B | Bilateral monetary consideration obligation through IFSC Banking Unit | Financial Institutions must now both transact AND receive all monetary consideration only through an account maintained with a Banking Unit in IFSC. The previous wording used 'or', meaning only one direction was covered. Both inflows and outflows must now route through the IFSC Banking Unit. This requires a payment flow review with treasury. | Process / Cross-functional | High | High | 60 days | Principal Officer (Compliance oversight) / Treasury (primary owner) | None | Not Started | Compliance owns the obligation; treasury owns the implementation. Payment flow mapping exercise required.

## 02 - Control Impact Assessment
Control Impact Assessment ¦ January 2026 Amendments ¦ New = control does not exist Modified = exists but needs change Retired = no longer required
Req ID | Clause | Control ID | Existing Control (if any) | Impact | Control Change Required | Evidence Required After Change | Owner | Target Date | Status
REQ-01 | 4.1(d) | CTL-KYC-01 | Customer Risk Rating - internal records maintained in KYC system | Modified | Add a field-level access restriction in the KYC system so that customer-facing staff cannot view the risk rating field. Update RM response guide to include scripted language for customer queries about account status. | Updated SOP section + training attendance record + system screenshot showing access restriction | Compliance Executive | 30-Apr-2026 | Not Started
REQ-02 | 5.3(b) | CTL-KYC-02 | CDD Completion Tracking - 30-day window monitored informally | Modified | Formalise the breach notification process. Create a standard escalation note template for cases where the 30-day window is breached. Add a Governing Body notification step to the CDD tracking SOP. | Breach notification template + updated SOP + evidence of Governing Body reporting in Board minutes (where applicable) | Principal Officer | 30-Apr-2026 | Not Started
REQ-03 | 5.6 GN(9) | CTL-EDD-01 | EDD Process - applied to high-risk customers | Modified | EDD must now also be triggered for all NR customers where the beneficial owner is an Indian national, irrespective of risk rating. Add this as a mandatory EDD trigger in the CDD checklist and onboarding SOP. Existing NR client book review required. | Updated CDD checklist with BO nationality field + evidence of EDD completion for affected clients + Principal Officer sign-off on review exercise | Compliance Executive | 30-Apr-2026 | Not Started
REQ-04 | 5.11 provison | CTL-KYC-03 | Periodic KYC Review - scheduled per standard 1/3/5 year cycle | Modified | Re-segment resident Indian clients with FG relationships to the new 2/8/10 year cycle. Where FG and IBU ratings differ, apply stricter cycle. Update KYC system scheduling or tracking tool accordingly. | Updated client segmentation report + revised KYC review schedule + system configuration evidence | Compliance Executive | 30-Jun-2026 | Not Started
REQ-05 | 5.11 explanation | CTL-GOV-01 | KYC Policy - internal document, last updated informally | Modified | Uplift the internal KYC policy to include a formal section on periodic review periodicities. Take through Governing Body for approval. Minute the approval. | Updated KYC policy document with version control + Board or committee meeting minutes showing approval | Principal Officer | 30-Apr-2026 | Not Started
REQ-06 | 5.11(c)(vii) | CTL-KYC-04 | None - no formal mechanism exists for customer-triggered document updates | New | Create a control requiring clients to be notified of their obligation to submit updated documents within 30 days of any change. Build a tracking mechanism (spreadsheet or system flag) to monitor receipt. Add to standard client onboarding communications. | Client communication template + updated onboarding pack + tracking log showing document receipt dates | Compliance Executive | 30-Jun-2026 | Not Started
REQ-07 | 5.4.4(a) | CTL-KYC-05 | CDD Checklist for Legal Persons - covers company and partnership onboarding | Modified | Extend the CDD checklist to cover legal arrangements (trusts). Add a mandatory disclosure step requiring trustees to confirm their trustee status at onboarding. Update the SOP for trust client onboarding. | Updated CDD checklist with trust-specific section + sample completed checklist for a trust client | Compliance Executive | 30-Jun-2026 | Not Started
REQ-08 | 10.3(5)(a)(i) | CTL-STR-01 | STR Filing Process - internal target of 7 days from conclusion of suspicion | Modified | Remove the 7-day internal SLA. Define 'promptly' as within 48 hours of the Principal Officer concluding suspicion (recommended internal standard). Update the STR SOP, the investigation workflow, and the filing log SLA field. | Updated STR SOP with revised SLA definition + filing log showing prompt filing dates + Principal Officer sign-off | Principal Officer | 30-Apr-2026 | Not Started
REQ-09 | 5.10(a) proviso | CTL-KYC-06 | None - no specific PwD onboarding control exists | New | Add a step to the onboarding SOP requiring the reviewing officer to record reasons if a PwD application is declined. Create a standard rejection note template. Include in staff training. | Updated onboarding SOP + rejection note template + training record | Compliance Executive | 30-Jun-2026 | Not Started
REQ-10 | Annexure II | CTL-VCIP-01 | V-CIP Process - in place but based on previous Annexure II standards | Modified | Review current V-CIP infrastructure against revised standards: IP address controls, liveness check standards, data localisation requirements. Add OTP-based Aadhaar e-KYC as a permitted authentication method. Update V-CIP SOP and training. | Gap assessment document + updated V-CIP SOP + technology team sign-off + training record | Principal Officer | 30-Sep-2026 | Not Started
REQ-11 | 1.3.30 | CTL-KYC-07 | Document Acceptance Checklist - based on previous OVD definition | Modified | Update the document acceptance checklist to explicitly list equivalent e-documents as acceptable for proof of address. Add guidance on verifying digital signatures. Include in staff onboarding training. | Updated checklist + revised onboarding SOP section + training record | Compliance Executive | 30-Jun-2026 | Not Started
REQ-12 | 7.2B | CTL-TREAS-01 | None - payment flow not formally mapped from a compliance perspective | New | Compliance to initiate a payment flow review with treasury. Map all inflows and outflows. Confirm all monetary consideration routes through the IFSC Banking Unit account. Document findings. Remediate any gaps. | Payment flow mapping document signed by treasury + compliance review note + Principal Officer sign-off | Principal Officer + Treasury | 30-Jun-2026 | Not Started

## 03 - Implementation Tracker
Implementation Tracker ¦ Milestones: 30 days = 30 Apr 2026 60 days = 31 May 2026 90 days = 30 Jun 2026 Extended = 30 Sep 2026
Req ID | Clause | Subject | Owner | Milestone | Target Date | Dependency | Key Actions | Sign-off Required | Sign-off By | Completion Date | Status | Comments
REQ-05 | 5.11 explanation | KYC Policy - Governing Body approval | Principal Officer | 30 days | 30-Apr-2026 | None | 1. Draft updated KYC policy section on review periodicities 2. Submit to Principal Officer for review 3. Place on Board / Board committee agenda 4. Obtain approval and minute it | Governing Body | Board Secretary |  | Not Started | Must close before REQ-04 and REQ-06 can be completed.
REQ-01 | 4.1(d) | Risk categorisation confidentiality | Compliance Executive | 30 days | 30-Apr-2026 | None | 1. Draft updated RM response guide 2. Update client communication templates 3. Arrange system access review with IT 4. Run staff briefing session | Principal Officer | Principal Officer |  | Not Started | Low effort. Quick win. Complete in first two weeks.
REQ-02 | 5.3(b) | 30-day verification - Governing Body escalation | Principal Officer | 30 days | 30-Apr-2026 | REQ-05 | 1. Create breach notification template 2. Update CDD tracking SOP with escalation step 3. Test with one live case if available 4. Principal Officer signs off on updated SOP | Principal Officer | Principal Officer |  | Not Started | Notification template is a one-page document. Straightforward to build.
REQ-03 | 5.6 GN(9) | EDD for NR customers with Indian national BO | Compliance Executive | 30 days | 30-Apr-2026 | REQ-01 | 1. Pull list of all NR clients from CRM 2. Identify those with Indian national BOs 3. Trigger EDD review for affected clients 4. Update CDD checklist with BO nationality field 5. Principal Officer reviews and signs off | Principal Officer | Principal Officer |  | Not Started | Priority item. Depending on client book size, this could be 20 to 40 client reviews. Sequence carefully against other 30-day items.
REQ-08 | 10.3(5)(a)(i) | STR filing - 'promptly' replaces 7-day window | Principal Officer | 30 days | 30-Apr-2026 | None | 1. Define internal SLA for 'promptly' (recommend 48 hours from Principal Officer conclusion) 2. Update STR SOP with new SLA 3. Update filing log SLA field 4. Brief compliance team on change | Principal Officer | Principal Officer |  | Not Started | Links directly to A2 (STR Playbook). SLA definition is a judgment call - document the rationale.
REQ-04 | 5.11 proviso | New periodic review cycle for resident Indian FG clients | Compliance Executive | 60 days | 31-May-2026 | REQ-05 | 1. Identify all resident Indian clients with FG relationships 2. Re-segment per new 2/8/10 year cycle 3. Where FG and IBU ratings differ, apply stricter cycle 4. Update KYC review schedule 5. Configure KYC system if applicable | Principal Officer | Principal Officer |  | Not Started | Depends on REQ-05 (Board-approved policy) being closed first.
REQ-06 | 5.11(c)(vii) | Customer 30-day document update obligation | Compliance Executive | 60 days | 31-May-2026 | REQ-05 | 1. Draft client communication template explaining the 30-day obligation 2. Build tracking mechanism in KYC system or spreadsheet 3. Include in standard onboarding communications going forward 4. Update SOP | Principal Officer | Principal Officer |  | Not Started | Client-facing item. Legal or relationship team may want to review the communication template.
REQ-07 | 5.4.4(a) | Trust clients - trustee status disclosure at onboarding | Compliance Executive | 60 days | 31-May-2026 | REQ-05 | 1. Review existing trust client files for disclosure gaps 2. Update CDD checklist with trust-specific section 3. Update onboarding SOP 4. Brief relationship team | Principal Officer | Principal Officer |  | Not Started | Number of trust clients in book will determine workload. If low, this closes quickly.
REQ-09 | 5.10(a) proviso | PwD onboarding rejection - documented reasoning | Compliance Executive | 60 days | 31-May-2026 | None | 1. Draft rejection note template 2. Update onboarding SOP with mandatory documentation step 3. Include in staff training | Principal Officer | Principal Officer |  | Not Started | Low frequency item but regulatory sensitivity is real. Simple to build.
REQ-11 | 1.3.30 | E-documents accepted as OVD for proof of address | Compliance Executive | 60 days | 31-May-2026 | None | 1. Update document acceptance checklist 2. Add e-document verification guidance (digital signature check) 3. Update onboarding SOP 4. Staff briefing | Principal Officer | Principal Officer |  | Not Started | Positive change for clients. Relatively simple to operationalise.
REQ-12 | 7.2B | Bilateral monetary consideration - IFSC Banking Unit | Principal Officer + Treasury | 60 days | 31-May-2026 | None | 1. Compliance to formally notify treasury of the obligation 2. Treasury to map all payment inflows and outflows 3. Identify any flows not routed through IFSC Banking Unit 4. Remediate gaps 5. Compliance to review and sign off | Principal Officer + CFO | Principal Officer |  | Not Started | Treasury owns implementation. Compliance owns the obligation and the sign-off. Escalate to CFO if treasury does not engage within 10 days.
REQ-10 | Annexure II | V-CIP expanded standards | Principal Officer | 90 days / Extended | 30-Sep-2026 | REQ-05 | 1. Conduct gap assessment of current V-CIP setup against revised Annexure II 2. Engage technology team on IP controls, liveness check standards, data localisation 3. Add OTP-based Aadhaar e-KYC as permitted method 4. Update V-CIP SOP 5. Staff training | Principal Officer + Technology | Principal Officer |  | Not Started | Longest lead time item due to technology dependency. Start gap assessment in Month 1 even if implementation is Month 3.

## 04 - RACI Matrix
RACI Matrix ¦ R = Responsible (does the work) A = Accountable (owns the outcome) C = Consulted (provides input) I = Informed (kept updated)
Req ID | Subject | Principal Officer | Compliance Executive 1 | Compliance Executive 2 | Treasury / Finance | Relationship Manager | Technology Team | Governing Body
REQ-01 | Risk categorisation confidentiality | A/C | R | I | I | C | C | I
REQ-02 | 30-day verification - GB escalation | A/R | C | I | I | I | I | I
REQ-03 | EDD for NR clients - Indian national BO | A | R | C | I | C | I | I
REQ-04 | New periodic review cycle - FG clients | A | R | C | I | I | C | I
REQ-05 | KYC Policy - Governing Body approval | A/R | C | I | I | I | I | A
REQ-06 | Customer 30-day document update | A | R | C | I | C | I | I
REQ-07 | Trust clients - trustee disclosure | A | R | C | I | C | I | I
REQ-08 | STR filing timeline - 'promptly' | A/R | C | C | I | I | I | I
REQ-09 | PwD onboarding rejection documentation | A | R | C | I | C | I | I
REQ-10 | V-CIP expanded standards | A | C | R | I | I | R | I
REQ-11 | E-documents as OVD | A | R | C | I | C | I | I
REQ-12 | Bilateral monetary consideration | A/C | I | I | R | I | I | I

## 05 - SOP Impact Register
SOP Impact Register ¦ Tracks which SOPs need to be created or updated as a result of the January 2026 amendments
SOP ID | SOP Name | Action Required | Linked Req IDs | Key Changes to Make | Owner | Target Date | Review / Approval | Status
SOP-KYC-01 | Customer Due Diligence and Onboarding SOP | Update | REQ-01, REQ-03, REQ-07, REQ-09, REQ-11 | Add RM response guidance on risk rating confidentiality. Add EDD trigger for NR clients with Indian national BOs. Add trust-specific CDD section with trustee disclosure step. Add PwD rejection documentation requirement. Update OVD section to include equivalent e-documents. | Compliance Executive 1 | 30-Jun-2026 | Principal Officer | Not Started
SOP-KYC-02 | Periodic KYC Review SOP | Update | REQ-04, REQ-05, REQ-06 | Update review periodicity tables to reflect new FG client cycle (2/8/10 years). Add stricter-cycle rule where FG and IBU ratings differ. Add client notification process for 30-day document update obligation. | Compliance Executive 1 | 31-May-2026 | Principal Officer | Not Started
SOP-KYC-03 | CDD Breach and Escalation SOP | Create (New) | REQ-02 | New SOP covering what happens when the 30-day verification window is breached. Include breach notification template. Define Governing Body reporting step. Define who prepares the notification and within what timeframe. | Principal Officer | 30-Apr-2026 | Principal Officer | Not Started
SOP-STR-01 | Suspicious Transaction Reporting SOP | Update | REQ-08 | Remove 7-day SLA reference. Define 'promptly' as 48 hours from Principal Officer conclusion of suspicion. Update filing log SLA field. Update escalation steps if investigation is running close to the filing trigger point. | Principal Officer | 30-Apr-2026 | Principal Officer | Not Started
SOP-VCIP-01 | Video Customer Identification Process SOP | Update | REQ-10 | Add OTP-based Aadhaar e-KYC as a permitted authentication method. Update IP address control requirements. Update liveness check and anti-deepfake standards. Update data localisation requirements. Update NRI jurisdiction list. | Compliance Executive 2 | 30-Sep-2026 | Principal Officer + Technology | Not Started
SOP-TREAS-01 | Payment Flow and Monetary Consideration SOP | Create (New) | REQ-12 | New SOP documenting that all monetary consideration, both inflows and outflows, must route through the IFSC Banking Unit account. Include payment flow map as an annexure. Define who reviews payment flow compliance and at what frequency. | Principal Officer + Treasury | 31-May-2026 | Principal Officer + CFO | Not Started
SOP-KYC-04 | Internal KYC Policy | Update (Board Approval Required) | REQ-05 | Add formal section on KYC review periodicities including FG client cycle. Obtain Governing Body approval before any other REQ-04 or REQ-06 actions are completed. Maintain version history and approval evidence. | Principal Officer | 30-Apr-2026 | Governing Body | Not Started

## 06 - Capacity Impact Note
Capacity Impact Note ¦ Team: Principal Officer + 2 Compliance Executives ¦ Baseline: 12 regulatory change items across 90 days (Apr to Jun 2026)
Effort estimates below reflect working days for a compliance professional with moderate familiarity with the subject matter. They exclude any technology configuration time (which is owned outside the compliance team) and any Board calendar lead time. Where two executives are shown in the same milestone window, work is assumed to be split. The Principal Officer is assumed to be spending approximately 30% of available time on this programme alongside BAU responsibilities.
Req ID | Subject | Owner | Milestone | Milestone Window | Concurrent Items in Window | Capacity Flag | Sequencing Note | BAU Impact | Automation Potential | Escalation Trigger
REQ-05 | KYC Policy - GB approval | Principal Officer | 30 days | Apr 2026 | 4 items in 30-day window | Medium | Must be completed first. Board calendar slot needed - book immediately. | Low | Low | If Board slot unavailable before 30-Apr, escalate to Principal Officer immediately. Do not let other items queue behind this.
REQ-01 | Risk categorisation confidentiality | Comp Exec 1 | 30 days | Apr 2026 | 4 items in 30-day window | Low | Quick win. Complete in Week 1 to free capacity. | Low | Low | None - straightforward item.
REQ-02 | 30-day verification escalation | Principal Officer | 30 days | Apr 2026 | 4 items in 30-day window | Low | Template-based. Principal Officer can complete alongside REQ-05. | Low | Medium - reminder automation feasible | None.
REQ-08 | STR timeline - promptly | Principal Officer | 30 days | Apr 2026 | 4 items in 30-day window | Low | SLA definition decision needed. Once made, SOP update is fast. | Low | Low | If Principal Officer cannot define SLA within 10 days, escalate to Board Risk Committee for guidance.
REQ-03 | EDD - Indian national BO | Comp Exec 1 | 30 days | Apr 2026 | 4 items in 30-day window | HIGH | Highest effort item in Month 1. Workload depends on client book size. May need Exec 2 support. | High | Medium | If affected client count exceeds 30, flag to Principal Officer for phased completion with Board notification.
REQ-04 | New periodic review cycle - FG | Comp Exec 1 | 60 days | May 2026 | 5 items in 60-day window | Medium | Depends on REQ-05 closure. System config may add lead time. | Medium | High - scheduling automation high value | If system config required and IT cannot deliver by 31-May, escalate to Principal Officer for manual interim process.
REQ-06 | Customer 30-day doc update | Comp Exec 1 | 60 days | May 2026 | 5 items in 60-day window | Low | Client communication template is the main output. | Low | Medium | None.
REQ-07 | Trust clients - trustee disclosure | Comp Exec 2 | 60 days | May 2026 | 5 items in 60-day window | Low | Exec 2 can run this in parallel with other items. | Low | Low | If trust client count is above 20, flag early.
REQ-09 | PwD onboarding documentation | Comp Exec 2 | 60 days | May 2026 | 5 items in 60-day window | Low | Smallest item in the register. Complete early in Month 2. | Low | Low | None.
REQ-11 | E-documents as OVD | Comp Exec 2 | 60 days | May 2026 | 5 items in 60-day window | Low | Checklist update. Straightforward. | Low | Low | None.
REQ-12 | Bilateral monetary consideration | Principal Officer + Treasury | 60 days | May 2026 | 5 items in 60-day window | Medium | Treasury engagement is the risk. Compliance must formally notify treasury in Week 1 of Month 2. | Medium | Low | If treasury does not respond within 10 days of notification, escalate to CFO.
REQ-10 | V-CIP expanded standards | Comp Exec 2 + Tech | 90 days+ | Sep 2026 | 1 item in extended window | Low | Technology dependency. Gap assessment in Month 1. Implementation in Month 3. | Low | Medium | If technology team cannot confirm timeline by end of Month 1, escalate to Principal Officer.